## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2231-swen-261-02-3 we're better
Testing Team Name | fill in when doing cross-team testing

## Test Plan
| Acceptance Criterion | Sprint 3 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed)
As a helper I want to see a list of needs so that I choose what to contribute to. | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page. | Pass | ALP 11/13 |  | DID NOT DO FOR SPRINT 2
| Given that I am not on the Needs page when I choose the Needs page then I am taken to the Needs page. | Pass | ALP 11/13
| Given that I am on the Needs page when there are no needs in the cupboard I see a message indicating that that there are no needs available to contribute. | Pass | ALP 11/13 - Does not show any message - fixed (11/19)
| Given that I am on the Needs page when there are needs in the cupboard then I see each need and short description. | Pass | ALP 11/13
| Given that I am on the Needs page when there are needs in the cupboard then I see a means to add each need to my funding basket. | Pass | ALP 11/13
As a helper I want to have a basket so I can contribute to the fund | Given that I am on the u-fund site when I want to add any of the Needs to my basket then I can press a button to do so | Pass | ALP 11/13
| Given that I am on the u-fund site when I want to see my basket then there is a way to navigate there | Pass | ALP 11/13
| Given that I can see my basket when I want to checkout everything in my basket then I can press a button to do so | Pass | ALP 11/13
| Given that I can see my basket when I want to remove any needs then there is a button to do so | Pass | ALP 11/13
As an admin I want to be able to edit, add, or remove needs | Given that I am logged in as an admin when I am on the main page then I should see a list of needs in my cupboard | Pass | ALP 11/13
| Given that I am logged in as an admin when I want to edit a need there is a button to do so | Pass | ALP 11/13
| Given that I am logged in as an admin when I want to add a need there is a button to do so | Pass | ALP 11/13
| Given that I am logged in as an admin when I want to remove a need there is a button to do so | Pass | ALP 11/13
As a helper/admin I want to login so I can have access to my own account | Given that the given username and password match when I press login then it logs in to the correct account | Pass | ALP 11/13
| Given that the given username and password doesn't match when I press login I am given some sort of error and nothing happens | Pass | ALP 11/13 - no error given - fixed (11/16)
| Given that an account name doesn't exist when I want to create an account then there is a button to do so | Pass | ALP 11/13
| Given that an account name doesexist when I want to create an account an error is given, and nothing happens | Pass | ALP 11/13 - no error given - fixed (11/16)
As a helper I want to search the list of needs so I can find a specific need | Given that I can see a list of needs when I want to search for a need then there is a search bar to do so | Pass | ALP 11/13 - no search bar present - added(11/18)
| Given that there is a need with a given name when I search for it then the need is brought up | Pass | ALP 11/13 - no search bar present - added(11/18)
| Given there is not a need with a given name when I search for it then nothing is brought up | Pass | ALP 11/13 - no search bar present - added(11/18)
As a helper I want to have access to account settings so I can change my username/password and delete my account | Given that I am on the u-fund site when I want to access my account settings then there is a tab to do so | Pass | ALP 11/13 - no account settings present - added(11/18)
| Given a desired username isn't taken when I want to change mine to it then there is a button to do so and the name is changed | Pass | ALP 11/13 - no account settings present - added(11/18)
| Given a desired username is taken when I want to change mine to it then there is a button to do so but an error is given and nothing happens | Pass | ALP 11/13 - no account settings present - added(11/18)
| Given a password of an acceptable string when I want to change my password to it then there is a button to do so and the password is changed | Pass | ALP 11/13 - no account settings present - added(11/18)
| Given a password of an unacceptable string when I want to change my password to it then there is a button to do so but an error is given and nothing happens | Pass | ALP 11/13 - no account settings present - added(11/18)
| Given I am a helper when I want to delete my account then there is a button to do so and the account is deleted | Pass | ALP 11/13 - no account settings present - added(11/18)
As a helper/admin I want to see the number of contributors for each need | Given that a need was helped when I see the need in the list then the number of contributors increased | Pass | ALP 11/13 - no contributors present - added (11/16)
| Given that a need was helped by an account twice when I see the need in the list then the number of contributors only increased once | Pass | ALP 11/13 - no contributors present - added (11/16)
BUG LIST
| Negative quantities for creating need and adding need | Pass | fixed (11/16)
| Does not remove quantities from funding basket if they are removed in the admin view | Pass | fixed (11/16)
| If you change the URL to anything other than admin, a blank page shows up | Pass | fixed (11/16)
| Funding basket is shared for all users | Pass | fixed (11/16)
| Can create needs with all the same information | Pass | fixed (11/16)
| You can enter e as a number but it doesn't give you an error if you try to confirm it (does not accept it still) | Pass | fixed (11/16)
| If you add an item to the basket and then create new need, you go back and the basket is cleared | Pass | fixed (11/16)
| If you add an item to the basket twice with different quantities, it has two of the item in the basket and they both have the quantity of the second entry | Pass | fixed (11/16)
| If you have the same error as directly before and you try to remove the second one from the basket, the first one's quantity changes to nothing and the total is NaN | Pass | fixed (11/16)
| If you have items in your basket and you remove them in the admin view, they are still present in the basket afterwards | Pass | fixed (11/16)